# HANDOFF.md: AI Influencer 7-Day Sprint

Written Oct 4, 2026 from a single Cowork conversation (started Sat Oct 3, 2026, ~2:22 PM PT). Owner: ASJ (DJ J Carbon). Everything below comes only from that conversation.

StarNest (17-part portfolio): did not come up in this conversation. Nothing about it is recorded here. See Open questions.

## 1. Project overview

### AI influencer project

What it is: recreating the flow from a YouTube "7-day AI influencer challenge" video (Claude + Higgsfield, 3 AI characters, Instagram, digital product sold via Stan Store; result: 23 sales × $12 = $276 revenue, $157.48 profit). ASJ is keeping the flow and changing the content.

The video's 10 steps, which this project mirrors:

- Spy on competition

- Generate character ideas

- Generate photos

- Map out viral content (scripts)

- Give them a voice

- Bring them to life (video)

- Launch accounts

- Unplanned check-in

- Start making money

- Count profits

Why: ASJ is strapped for cash ($19 on hand, $40 incoming). The goal is to see if this works and to generate $100 in sales by Sat Oct 10, 2026. That money funds ads afterward. Unlike the video, ASJ wants to keep growing all three characters past day 7, not stop.

Three characters (all Black, all openly AI):

| Character | Niche | Instagram | TikTok | Product (planned) |
| --- | --- | --- | --- | --- |
| Miss Pearl, 78, retired Vegas blackjack dealer, 3 ex-husbands | Comedy + money talk | @misspearlmoney | none yet | Miss Pearl's Petty Budget: printable budget planner w/ roast notes, $5 |
| Grandpa Eli, 91, retired farmer, rural Georgia | Health & wellness (habits, no cures) | @grandpaeliliveswell | none yet | 30-Day Old Ways Reset: one habit/day + tick tracker, $7 |
| Jade, 24, Oakland, stylist's assistant | Lifestyle + relationships | @jadegxlden | live (handle not given) | Situationship Detox: 14-day journal, $6 |

Current status (as of end of conversation):

- Plan doc published: "AI Influencer 7-Day Sprint" (Claude Docs artifact, https://claude.ai/code/artifact/2013090d-e0b6-4539-b803-7890fb40510f). This is the live source of truth.

- Character sheets: ASJ ran them in Gemini (implied, since ASJ then moved on to scene photos). Scene photos were in progress when the outfit issue came up. The prompt was fixed and 9 ready-made scene prompts were added.

- Instagram: all 3 accounts created with the usernames above. Bios were provided. Whether they've been pasted in is unconfirmed.

- TikTok: only Jade's account exists. TikTok forced phone verification, and ASJ's number is already used.

- Products: not built yet. Claude asked "tonight or first thing tomorrow?" and got no answer.

- Payhip, Higgsfield, Postiz connection for the new accounts: not done.

- No posts published yet. No sales.

### Competitor research (Step 1, done)

Reported AI-influencer income. All figures are self-reported or estimated, not audited:

| Creator | Niche | Audience | Reported income | Model |
| --- | --- | --- | --- | --- |
| Lil Miquela | Fashion/music | ~2.3–2.6M IG | ~$10M+/yr (estimate) | Brand deals, music, merch, licensing |
| Lu do Magalu | Retail/tech | 8–9.7M IG | $2.5M/yr ($34K/post) | Retailer spokesperson, sponsored posts |
| Yang Mun ("AI monk") | Wellness/spirituality | ~2.5M IG | $213K in 90 days (own screenshots) | $24 ebook, $50 course, $799/hr coaching. Reported as a scam (EBU Spotlight) |
| Kyra | Fashion/travel (India) | ~250K IG | ₹1.25–1.5 crore brand revenue | Brand deals |
| Aitana Lopez | Fitness/fashion | ~400K IG | €3K–10K/mo | Sponsorships, Fanvue |
| Unnamed Higgsfield operator | Lifestyle | 50K in 30 days | $12.5K/mo (self-reported) | Subscriptions, paid DMs, tips |
| Granny Spills | Comedy/life advice | ~2.2M IG | undisclosed | Brand placements, Cameo |
| Mother Satori | Health/longevity | unknown | undisclosed | Promotes a gut-detox drink (fake 108-yr-old persona) |

Niche pay (TikTok, InfluenceFlow): finance/business pays most (~$800–1,000 per 1M views, $5K–50K+ brand deals). Wellness is strong for digital products and affiliate commissions (10–30%). Fashion/lifestyle pays mid. Comedy pays least per view but grows reach.

Sources: instantdm.com/blog/how-ai-influencers-make-money-2026 · ryla.ai/en/blog/ai-influencer-income · creatorflow.so/blog/ai-influencers-instagram · influenceflow.io/resources/tiktok-creator-earnings-by-niche-the-complete-2026-guide · spotlight.ebu.ch/p/yang-mun-ai-influencer-scam

## 2. Decisions made

| Decision | Reason |
| --- | --- |
| AI is disclosed openly: "AI" in every bio + platform AI label on every post | ASJ: "I'm not trying to hide it from anybody." Platforms also penalize unlabeled AI. |
| Three niches: comedy (older woman), health & wellness (older man), lifestyle/relationships (young woman) | ASJ liked the video's setup (young lifestyle girl, glam older woman, health older man). |
| Grow all three past day 7 | ASJ wants to ramp up, not stop like the video did. |
| Characters are Black. Pearl is fair-skinned, Eli dark-skinned, Jade brown-skinned | ASJ wants an AI market for Black audiences. Claude recommended not watering it down, since it's an underserved gap. The range of skin tones also works as a built-in test. |
| No celebrity names in image prompts (Pearl's vibe described as Phylicia Rashad / Diana Ross elegance, prompt describes features only) | Image tools refuse or distort real-person prompts, and a lookalike risks reports. |
| Pearl does both money roasts and life-advice comedy, same voice | ASJ answered "both" in the doc comment thread. |
| Each scene gets a new outfit. Face, skin tone and hair stay the same. Signature details stay (Pearl's gold jewelry, Eli's beard, Jade's hoops) | Gemini was putting characters in the same clothes in every scene. |
| Primary offer: one cheap printable digital product per character ($5–7), plus a $12 bundle Friday | Sellable from day 1, built by Claude, $0 cost. |
| Payhip free plan instead of Stan Store | $0/mo + 5% per sale, vs. Stan's $29/mo. |
| $0 spend until money arrives. Then Higgsfield Starter (~$15/mo) only, not the $99 plan | Cash is $19. Higgsfield is only needed for talking videos and is optional at the start. |
| Weekend content = free tools: Gemini (or ChatGPT free) for images, CapCut free for video (photo + zoom + on-screen text + built-in voice) | No money until the transfer lands. |
| Don't use free tiers of Kling, Hedra, Vidu, Seedance for these accounts | Watermarks, and their free tiers ban commercial use. |
| No ads this week | No budget. Ads start only after ~$100 revenue. |
| Platforms: Instagram for all 3. TikTok for Jade only (for now) | TikTok forces a new phone number per account. |
| New accounts kept separate from DJ J Carbon accounts | ASJ suspects the DJ account has low reach (possible flag). Fresh, separate accounts avoid any link. |
| Don't buy SMS-verification numbers. Google Voice likely rejected | They get blocked or flagged. |
| Wednesday leader comparison uses Instagram numbers only | Jade has two platforms, which would skew a raw comparison. |
| Content rules: Eli gives habits, never cures, supplements or detox drinks. No fake reviews. No income claims from Pearl. No buying followers | Avoids FTC and platform trouble. Also contrasts with Mother Satori / Yang Mun. |
| Ironic $14 Miss Pearl candle = later product | ASJ's idea. Physical product, so it waits for cash (samples or print-on-demand). |

## 3. Actionable items (priority order)

Deadlines are PT. "Code" = Claude Code / Claude.

- 1. Build the 3 printable products (PDFs). Owner: Code

  - Next step: build Miss Pearl's Petty Budget ($5), 30-Day Old Ways Reset ($7), Situationship Detox (14-day journal, $6). Printable, in each character's voice. Eli's has no medical claims.

  - Depends on: nothing. Confirm timing with ASJ first (question was left unanswered).

  - Window: Sun Oct 4.

- 2. Proofread the products. Owner: ASJ · Depends on #1 · Sun Oct 4.

- 3. Finish scene photos in Gemini (9 ready-made prompts in §4.3). Owner: ASJ · Depends on character sheets · Sat Oct 3 night or Sun Oct 4.

- 4. Finish Instagram setup for all 3: paste bios (§7), set profile pic (best close-up from the sheet), switch to Professional → Creator, put "Jade" in Jade's Name field. Owner: ASJ · Now.

- 5. Switch Jade's TikTok to a Business account (Settings → Account → Switch to Business Account) so it can show a bio link. Owner: ASJ · Now.

- 6. Open a free Payhip account, list the 3 products, put each link in its bios (IG ×3, Jade TikTok). Owner: ASJ (Code can draft listing copy) · Depends on #1–2 · Sun Oct 4.

- 7. Write 5 scripts per character (prompt in §4.4). Owner: Code · Sun Oct 4.

- 8. Edit 3 videos per character in CapCut (photo + slow zoom + on-screen text + built-in voice). AI label on every post. Owner: ASJ · Depends on #3, #7 · Sun Oct 4.

- 9. Connect the new accounts to Postiz and schedule. Trial ends around Mon Oct 5. Fallback: Meta Business Suite (IG) and TikTok's desktop scheduler. Owner: ASJ (Code can schedule via the Postiz connector once accounts are connected) · Sun Oct 4.

- 10. Buy Higgsfield Starter (~$15) when the $40 lands. Optional, and could wait until the first sale. Owner: ASJ · Mon Oct 5 or later.

- 11. One talking intro video per character (10–20s, "I'm an AI, and here's why you should still listen"), prompts in §4.5 and §4.6. Owner: ASJ (Code writes lines) · Depends on #10 · Mon Oct 5.

- 12. Post 2/day per account, same video on IG + TikTok for Jade. Owner: ASJ · Mon Oct 5 onward.

- 13. Reply in character to every comment, ideally within an hour. Owner: ASJ · Daily from Tue Oct 6.

- 14. Fill in the tracker nightly (views, link clicks, sales, revenue per character) and send the numbers to Claude. Owner: ASJ · Nightly from Sun Oct 4.

- 15. Make 6 more videos. Owner: ASJ + Code (scripts) · Tue Oct 6.

- 16. Pick the leader (IG numbers only). The leader gets 2 posts for every 1 the others get. Nobody stops. Remake the leader's best video in 2 versions (new first line, same idea). Owner: Code analyzes, ASJ executes · Wed Oct 7.

- 17. Sales push: one openly-pitch video per character ("Comment PEARL and I'll send you the planner"). Pin a comment with the Payhip link on every video. DM the link to everyone who comments the keyword. Owner: ASJ (Code writes) · Thu Oct 8.

- 18. Offer a $12 bundle of all 3 on Payhip and mention it from the leading account. Owner: ASJ · Fri Oct 9.

- 19. Count it: revenue minus Higgsfield minus fees. ≥ $100 → small ad test on the leader's best video. < $100 → repeat the plan 7 more days with no new spending. Owner: ASJ + Code · Sat Oct 10.

- 20. Get a second phone number (cheap prepaid SIM or a family member's with permission) and add the leading character's TikTok. Owner: ASJ · after Wed Oct 7.

- 21. Later: ironic $14 Miss Pearl candle ("The candle you couldn't afford"). Owner: ASJ · after income exists.

## 4. Learned skills and workflows

### 4.1 Skill: ai-influencer-competitor-scan

- Description: Find top-earning AI influencers by niche and how they make money, before choosing a niche.

- When: starting a new AI-influencer or faceless account, or picking a new niche.

- Steps:

  - Web-search "highest earning AI influencers [year] income niche" and named examples. Fetch the source pages; don't trust snippets.

  - Build a table: creator · niche · audience · reported income · income source · monetization model.

  - Flag every figure as self-reported or estimated. Flag known scams and deceptive personas.

  - Add niche-level pay data (CPM per 1M views, brand-deal ranges).

  - Name the gap: the niche nobody's AI accounts cover (here, money/wealth).

### 4.2 Skill: ai-character-sheet

- Description: Generate a consistent photoreal AI character reference sheet in Gemini or ChatGPT.

- When: creating any new AI character.

- Steps: describe skin tone, age, features, hair, outfit. Never name a celebrity. Paste the template. If the result is too smooth or too young, reply "make her older, more natural wrinkles." Use a fresh chat per character so faces don't blend.

- Template:

Photorealistic character reference sheet of [WHO + LOOK]. Three views side by side: front close-up, 3/4 side, full body standing. Plain white studio background, soft even lighting, natural skin texture with real pores and wrinkles, no airbrushing, no text. Same face, hair and outfit in every view.

- Ready prompts:

Miss Pearl: Photorealistic character reference sheet of a glamorous 78-year-old fair-skinned Black woman with a warm golden undertone, elegant high cheekbones, soft silver curls in a voluminous blowout, red lipstick, cat-eye sunglasses pushed up on her head, layered gold jewelry, leopard-print silk robe. Three views side by side: front close-up, 3/4 side, full body standing. Plain white studio background, soft even lighting, natural skin texture with real wrinkles and pores, no airbrushing, no text. Same face, hair and outfit in every view.

Grandpa Eli: Photorealistic character reference sheet of a 91-year-old deep dark-skinned Black man from rural Georgia, bald head, full white beard, kind eyes with deep smile lines, weathered working hands, faded denim overalls over a white henley, straw hat in hand. Three views side by side: front close-up, 3/4 side, full body standing. Plain white studio background, soft even lighting, natural skin texture with real wrinkles and pores, no airbrushing, no text. Same face, beard and outfit in every view.

Jade: Photorealistic character reference sheet of a 24-year-old medium brown-skinned Black woman from Oakland, long knotless braids, gold hoop earrings, light natural makeup, oversized vintage graphic tee, baggy cargo pants, chunky sneakers. Three views side by side: front close-up, 3/4 side, full body standing. Plain white studio background, soft even lighting, natural skin texture with real pores, no airbrushing, no text. Same face, hair and outfit in every view.

### 4.3 Skill: ai-character-scenes

- Description: Place a character in new scenes with new outfits while keeping the face consistent.

- When: after the character sheet exists.

- Steps: upload that character's sheet, then paste one prompt at a time. If the face drifts, re-upload the sheet and add "same exact face as the reference." Always specify a new outfit and keep one signature detail.

- Generic template (fixed version):

Using the attached character as reference, same face, skin tone and hair, but a NEW outfit that fits the scene, place them in: [SCENE]. Vertical 9:16, candid phone-camera look, natural light, realistic. Make 4 versions: [scene 1], [scene 2], [scene 3], [scene 4].

- Scene ideas: Pearl: casino bar, pink kitchen, poolside lounger, back seat of a Cadillac. Eli: porch rocker, garden rows, wood stove kitchen, dirt road at sunrise. Jade: podcast mic setup, Lake Merritt bench, thrift store, bathroom mirror.

- Ready prompts:

Pearl 1: Using the attached woman as reference, keep her exact face, fair skin with golden undertone, and silver curls. New outfit: black sequin wrap dress, layered gold necklaces, oversized cat-eye sunglasses. She sits at a dim Las Vegas casino bar, martini in hand, smirking at the camera, slot machines glowing behind her. Vertical 9:16, candid phone photo, warm neon light, photorealistic, natural skin texture, no text.

Pearl 2: Using the attached woman as reference, keep her exact face, fair skin with golden undertone, and silver curls. New outfit: pink satin pajama set, gold hoop earrings, silk scarf tied over her curls. She stands in a retro pink kitchen holding a coffee mug, one eyebrow raised, unpaid bills stacked on the counter. Vertical 9:16, candid phone photo, morning window light, photorealistic, natural skin texture, no text.

Pearl 3: Using the attached woman as reference, keep her exact face, fair skin with golden undertone, and silver curls. New outfit: white linen pantsuit, wide-brim sun hat, gold bangles, tortoiseshell sunglasses. She lounges in the back seat of a vintage cream Cadillac convertible, arm draped over the door, laughing. Vertical 9:16, candid phone photo, golden hour sunlight, photorealistic, natural skin texture, no text.

Eli 1: Using the attached man as reference, keep his exact face, deep dark skin, bald head and full white beard. New outfit: red flannel shirt, tan work pants, suspenders. He sits in a wooden rocking chair on a weathered farmhouse porch in rural Georgia, holding a mason jar of water, looking at the camera with a calm smile. Vertical 9:16, candid phone photo, soft morning light, photorealistic, natural skin texture, no text.

Eli 2: Using the attached man as reference, keep his exact face, deep dark skin, bald head and full white beard. New outfit: faded denim overalls over a white henley, straw hat, work gloves. He kneels between rows of collard greens and tomatoes in a backyard garden, holding a fresh-picked tomato toward the camera. Vertical 9:16, candid phone photo, bright midday sun, photorealistic, natural skin texture, no text.

Eli 3: Using the attached man as reference, keep his exact face, deep dark skin, bald head and full white beard. New outfit: brown knit cardigan over a plaid shirt, reading glasses on his nose. He stands at a cast-iron wood stove in an old farmhouse kitchen, stirring a pot of beans, steam rising. Vertical 9:16, candid phone photo, warm lamp light, photorealistic, natural skin texture, no text.

Jade 1: Using the attached woman as reference, keep her exact face, medium brown skin and long knotless braids. New outfit: cropped black hoodie, gold hoop earrings, gold name necklace. She sits at a home podcast setup with a mic on a boom arm and LED lights behind her, mid-sentence, hand raised like she's making a point. Vertical 9:16, candid phone photo, purple and pink LED glow, photorealistic, natural skin texture, no text.

Jade 2: Using the attached woman as reference, keep her exact face, medium brown skin and long knotless braids. New outfit: oversized vintage denim jacket, white tank top, baggy jeans, gold hoops, chunky sneakers. She sits on a bench at Lake Merritt in Oakland holding an iced coffee, looking off to the side, the lake and the necklace of lights behind her. Vertical 9:16, candid phone photo, golden hour, photorealistic, natural skin texture, no text.

Jade 3: Using the attached woman as reference, keep her exact face, medium brown skin and long knotless braids pulled into a high bun. New outfit: fitted brown slip dress, gold hoops, small gold rings. She takes a mirror selfie in a bathroom, phone covering part of her face, getting ready for a date, makeup laid out on the counter. Vertical 9:16, candid phone photo, warm vanity light, photorealistic, natural skin texture, no text.

### 4.4 Skill: ai-character-scripts

- Description: Write short-form scripts in character with a soft product pitch.

- When: each content batch (5 per character).

Write 5 short-form video scripts for [NAME] ([niche], [hook]). Each under 25 seconds: a 1-line hook that stops the scroll in the first 2 seconds, 3-4 lines of body, a soft call to action for [PRODUCT]. Include on-screen text for each. No medical claims, no promises of income. Keep it in character.

- Hooks: Pearl alternates money roasts ("girl, you spent $14 on a candle?") and life-advice comedy ("Husband #2 taught me this"), same voice. Eli: "Things we did in 1950 that y'all pay apps for now." Jade: podcast-style storytime, "babe, he was using you."

### 4.5 Skill: higgsfield-talking-video

- Description: Make a talking-to-camera clip from the character sheet (once Higgsfield is bought).

[Upload character sheet] Vertical 9:16, 1080p. [NAME] speaks directly to camera in [SCENE], natural head movement, casual handheld feel. Script: "[LINE]"

### 4.6 Skill: character-voice-descriptions (paste into Higgsfield voice settings)

- Pearl: raspy, smoky older woman, slow drawl, dry delivery, laughs at her own jokes

- Eli: warm, deep older Southern man, unhurried, a little gravel

- Jade: young Bay Area woman, quick, playful, lots of upward inflection

### 4.7 Skill: zero-budget-ai-influencer-launch

- Description: Launch disclosed AI influencer accounts and sell a digital product with ~$0.

- Steps:

  - Characters + sheets + scenes (4.2, 4.3).

  - IG accounts: bio with "AI" + Professional → Creator. TikTok: Business account so the link works before 1,000 followers. A personal account needs 1,000 followers for a link. Workarounds: pinned comment, AutoDM keyword, link to IG.

  - Products built by Claude → Payhip free → link in bio.

  - Weekend content in CapCut (photo + zoom + text + built-in voice). Talking videos later via Higgsfield Starter.

  - 2 posts/day/account. Cross-post the same video. AI label always.

  - Reply to comments in character. Track nightly.

  - Mid-week: leader gets 2:1 posts. Thu: keyword-comment pitch + pinned link + DMs. Fri: bundle. Sat: count.

- Math: $100 ≈ 15–18 sales at $5–7 after fees ≈ 20,000–50,000 views of pitch-carrying posts in a week. Treat it as a coin flip.

### 4.8 Skill: instagram-ai-bio

- Description: IG bio for a disclosed AI character, under 150 chars.

- Pattern: line 1 = "AI ___" + emoji · line 2 = age/backstory · line 3 = what they do · line 4 = product name + ⬇️. Name field: "Name | AI Role". Leave the link empty until the Payhip link exists.

### 4.9 Skill: tiktok-extra-account-signup

- Steps: Profile → username → Add account → Sign up → "Use phone or email" → Email tab, with a separate Gmail per character. Or try Google sign-in. If TikTok still forces a phone: don't use SMS-rental or Google Voice numbers. Use a second real number (prepaid SIM or a family member's with permission), or stay IG-only.

- Observed result: email sign-up still forced phone verification. Only Jade's account was created.

### 4.10 Workflow: daily tracker

Columns: Date · Character · Posts · Views · Link clicks · Sales · Revenue ($). Fill nightly. Compare characters on IG only.

## 5. Code and configuration

No code, scripts, schemas or config files were written. The only tool/API calls with lasting relevance:

Postiz integration list call (via the Postiz MCP connector, integrationList, no params). Returned the currently connected Postiz channels. None of the new AI accounts are connected yet:

[

{"name": "DJ J Carbon Th3 Alkhemist", "platform": "instagram-standalone"},

{"name": "Cafe Carbon",                "platform": "tiktok-business"},

{"name": "DJ J Carbon",                "platform": "youtube"}

]

All prompts are in §4.

## 6. Architecture and plans

Claude (characters, scripts, product PDFs, analysis)

│

├─► Gemini app (free): character sheets → scene images

│        │

│        ▼

├─► CapCut (free): photo + zoom + on-screen text + built-in voice → 9:16 videos

│   Higgsfield Starter (~$15, from Mon if bought): talking videos + voices

│        │

│        ▼

├─► Scheduling: Postiz (trial ending ~Mon Oct 5) → fallback Meta Business Suite (IG) + TikTok desktop scheduler

│        │

│        ▼

│   Instagram: @misspearlmoney · @grandpaeliliveswell · @jadegxlden

│   TikTok: Jade only (Business account)

│        │  bio link

│        ▼

└─► Payhip free store (3 products + $12 bundle) → sales → nightly tracker → Wed leader pick → Sat count → ads if ≥ $100

- Plan doc (source of truth): Claude Docs artifact "AI Influencer 7-Day Sprint", https://claude.ai/code/artifact/2013090d-e0b6-4539-b803-7890fb40510f. Contains goal/math, character table, tool table, day-by-day checklist (ASJ has ticked "lock names"), all prompts, tracker, rules, and the candle note.

- Session project: "Ai creators" (claude.ai Project). This handoff is saved there.

- File locations: character sheets and scene images live in ASJ's Gemini chats / phone. No local folder was set up.

- Separation rule: keep the AI accounts separate from the DJ J Carbon / Cafe Carbon accounts. Create them on phone over cellular data.

## 7. Accounts, tools and handles (names only)

- Instagram: @misspearlmoney · @grandpaeliliveswell · @jadegxlden

- TikTok: Jade (handle not given in conversation)

- Existing (ASJ's, not part of this project): DJ J Carbon Th3 Alkhemist (IG), Cafe Carbon (TikTok business), DJ J Carbon (YouTube), all connected in Postiz

- Tools: Claude / Cowork, Claude Docs, Google Gemini app, ChatGPT (alt), CapCut, Higgsfield (planned), Payhip (planned), Postiz, Meta Business Suite, TikTok desktop scheduler

- Rejected/avoided: Stan Store ($29/mo), Higgsfield $99 plan, free tiers of Kling / Hedra / Vidu / Seedance, SMS-rental numbers, Google Voice for TikTok

- Bios:

  - Miss Pearl | AI Auntie: AI auntie with real opinions 🎰 / 78. Ex-Vegas dealer. 3 ex-husbands. / I roast your spending AND your man. / Petty Budget planner ⬇️ (Category: Comedian)

  - Grandpa Eli | AI Grandpa: Your AI grandpa 🌾 / 91. Georgia farm boy. / Old ways, simple habits. No pills, no gimmicks. / 30-Day Old Ways Reset ⬇️ (Category: Health/Beauty)

  - Jade | AI Girl, Real Tea: AI girl, real tea ☕ / 24. Oakland. / Situationships, red flags & glow-ups. / Situationship Detox ⬇️ (Category: Creator)

## 8. Open questions and blockers

- Products timing: build tonight (Oct 3) or Sun morning? Unanswered.

- TikTok for Pearl and Eli: blocked on a second phone number.

- The $40: first described as a TikTok payout expected Monday, later as a bank transfer arriving later. Arrival date unconfirmed. This gates the Higgsfield purchase.

- Higgsfield Starter price: ~$15/mo per third-party sources. Confirm at checkout.

- Postiz: about 2 trial days left as of Oct 3. Unknown whether the trial allows adding 4 more channels, and whether ASJ will pay after.

- Setup status unconfirmed: whether IG bios are pasted, IG accounts switched to Creator, Jade's TikTok switched to Business, and Jade's TikTok handle.

- Character sheets / scene images: finished? Not confirmed. No files shared with Claude.

- DJ J Carbon low TikTok reach: cause unknown (content vs. account vs. suspected IP flag). Not in scope here, but ASJ wants to avoid repeating it.

- StarNest (17-part portfolio): not discussed in this conversation. No info to hand off.

- Approval rule: the request mentioned "nothing sent without my approval," but it wasn't stated in this conversation. Confirm with ASJ. Default: Code doesn't post, schedule or publish without ASJ's OK.

- Payhip store structure: one store with a product link per bio vs. separate stores per character. Not decided.

## 9. First 3 things for Code to do

- Confirm the current state with ASJ (open questions 1, 3, 6, 7, 10). Then read the plan doc (artifact link in §6) for any edits ASJ made since. ASJ has been ticking boxes in it.

- Build the 3 printable PDF products (Miss Pearl's Petty Budget $5, 30-Day Old Ways Reset $7, Situationship Detox $6) in each character's voice. Disclose AI. Eli's has no medical claims. Deliver for ASJ to proofread, then draft the Payhip listing copy.

- Write the first script batch: 5 scripts per character using §4.4, with Pearl alternating money roasts and life advice. Include on-screen text, ready for ASJ to edit in CapCut for Sunday's 9 posts.

## Session update - 2026-10-04 08:43 PDT (Sun)

Covers only what happened after the original handoff above was written: ASJ's answers to the open questions, ASJ's instructions for this update, and the checks Claude ran while making it. No product, post, upload or purchase has happened since.

### Changes since the previous handoff

- §8 Q1 / §3 item 1 (products timing): resolved. ASJ said "build the products tonight" (Sun Oct 4 evening). Still not built at the time of this update.

- §8 Q3 (the $40): resolved and corrected. There are two separate $40 amounts: a $40 TikTok payout arriving tomorrow (Mon Oct 5) and a separate $40 bank transfer (arrival date not given).

- §8 Q2 / §3 item 20 (second phone number): ASJ has no second phone number. Pearl and Eli stay Instagram-only with no date set. Item 20 is on hold.

- §3 item 5, §4.7 step 2, §6 diagram ("TikTok: Jade only (Business account)"), and the Decisions row about Jade's TikTok link: out of date. Jade's TikTok is still a personal account. ASJ says switching needs an LLC/EIN, and ASJ has neither. A third-party source says TikTok started requiring business verification documents (business license, incorporation certificate or EIN letter) in 2026 (source). So Jade has no clickable TikTok bio link until 1,000 followers.

- §3 item 6 ("put each link in its bios … Jade TikTok"): partly out of date. The TikTok part can't be done yet. Instagram links still apply.

- §8 Q10 (approval rule): deferred by ASJ. ASJ will set it "at a later day after testing." Standing instruction for now: do not send, publish or purchase anything.

- §6 "File locations": out of date. HANDOFF.md now also exists as a project doc (claude/HANDOFF.md in the "Ai creators" Project), plus a backup file (see §5 of this update).

- §9 item 1 (confirm state): partly done. Q1, Q3, Q10 answered, plus the phone and Jade account status. Still unconfirmed: IG bios pasted, IG Creator switch, Jade's TikTok handle, character sheets and scene images.

### 1. Project overview

#### AI influencer project

- What and why: unchanged from the original handoff. Three openly-AI Black characters (Miss Pearl, Grandpa Eli, Jade), each selling one cheap printable product. Goal is $100 in sales by Sat Oct 10, 2026 to fund ads, then keep growing all three.

- Status now:

  - Instagram: 3 accounts exist (@misspearlmoney, @grandpaeliliveswell, @jadegxlden).

  - TikTok: Jade only, personal account (no bio link until 1,000 followers).

  - Products: to be built tonight (Sun Oct 4) by Code. Not started at the time of this update.

  - Payhip, Higgsfield, Postiz hookup for the new accounts: not done.

  - No posts, no sales.

  - Money: $19 on hand, plus $40 TikTok payout Mon Oct 5, plus a separate $40 bank transfer (date unknown). Up to ~$99 once both land.

  - Plan doc "AI Influencer 7-Day Sprint": no edits since Claude's last write (doc revision 25 checked at this update).

#### StarNest (17-part portfolio)

- Still not discussed in this conversation. Nothing to hand off.

### 2. Decisions made (new or changed this session)

| Decision | Reason |
| --- | --- |
| Build the 3 products tonight (Sun Oct 4) | ASJ's answer to the open timing question. |
| Jade's TikTok stays a personal account | ASJ has no LLC/EIN, and the Business switch reportedly needs business verification. |
| Pearl and Eli stay Instagram-only, with no end date | ASJ has no second phone number. |
| Jade's TikTok sends buyers via a pinned comment with the Payhip link, "link in my IG bio," and keyword-comment → DM, not a bio link | Personal accounts get no bio link under 1,000 followers. These workarounds came from the original research (§4.7). |
| Do not send, publish or purchase anything until ASJ sets the approval rule | ASJ's instruction for this update. ASJ will define the rule after testing. |
| Budget ceiling this week is up to ~$99 ($19 + $40 + $40), still no ads | Both $40 amounts are confirmed. The ads-after-$100 rule is unchanged. |
| Unchanged: AI disclosed openly; Payhip free over Stan Store; Higgsfield Starter (~$15) optional, never the $99 plan; free tools for content; Black characters (Pearl fair-skinned, Eli dark-skinned, Jade brown-skinned); Pearl does money roasts + life advice; Eli never gives health claims | See original §2. |

### 3. Actionable items (priority order, full current list)

"Code" = Claude / Claude Code. Times are PT.

- 1. Build the 3 printable PDF products. Owner: Code. Next step: build Miss Pearl's Petty Budget ($5), 30-Day Old Ways Reset ($7, habits only, no medical claims), Situationship Detox (14-day journal, $6), each in the character's voice with AI disclosed. Save the files and deliver them to ASJ. Do not upload anywhere. Depends on: nothing. Window: tonight, Sun Oct 4.

- 2. Proofread the products. Owner: ASJ. Depends on #1. Window: Sun Oct 4 night / Mon Oct 5.

- 3. Draft Payhip listing copy (title, description, price for each product, plus the $12 bundle). Owner: Code. Depends on #1. Draft only, ASJ posts it. Window: with #1.

- 4. Write 5 scripts per character (§4.4 prompt, with on-screen text). Pearl alternates money roasts and life advice. Jade's TikTok versions end with the workaround CTA (comment keyword / link in IG bio), not "link in bio." Owner: Code. Window: Sun Oct 4.

- 5. Finish scene photos in Gemini (9 prompts in original §4.3). Owner: ASJ. Window: Sun Oct 4.

- 6. Finish Instagram setup: paste bios, profile pics, Professional → Creator, "Jade" in Jade's Name field. Owner: ASJ. Window: now.

- 7. Open a free Payhip account, list the products, add links to the 3 Instagram bios. Owner: ASJ. Depends on #2, #3. Window: Mon Oct 5.

- 8. Jade TikTok link workaround: put "link in my IG bio" or "comment DETOX" in TikTok captions and pin a comment with the Payhip URL on each video. Owner: ASJ (Code writes captions). Depends on #7. Window: from first post.

- 9. Edit 3 videos per character in CapCut (photo + zoom + on-screen text + built-in voice, AI label on every post). Owner: ASJ. Depends on #4, #5. Window: Sun Oct 4 / Mon Oct 5.

- 10. Scheduling: connect the new accounts to Postiz before the trial ends (~Mon Oct 5), or use Meta Business Suite + TikTok's native scheduling. Owner: ASJ. Code must not schedule or post until ASJ approves. Window: Mon Oct 5.

- 11. Decide on Higgsfield Starter (~$15) after the TikTok payout lands Mon Oct 5. Optional, and could wait for the first sale. Code must not purchase. Owner: ASJ. Window: Mon Oct 5 or later.

- 12. One talking intro per character (if Higgsfield is bought). Owner: ASJ, Code writes lines. Depends on #11. Window: Mon Oct 5+.

- 13. Post 2/day per account (Jade cross-posted to TikTok). Owner: ASJ. Window: Mon Oct 5 onward.

- 14. Reply in character to every comment. Owner: ASJ. Window: daily from first post.

- 15. Nightly tracker (posts, views, link clicks, sales, revenue per character), numbers sent to Claude. Owner: ASJ. Window: nightly from first post.

- 16. Make 6 more videos. Owner: ASJ + Code (scripts). Window: Tue Oct 6.

- 17. Pick the leader on Instagram numbers only. 2:1 posting for the leader, nobody stops, remake their best video twice. Owner: Code analyzes, ASJ executes. Window: Wed Oct 7.

- 18. Sales push: keyword-comment pitch videos, pinned Payhip link, DM everyone who comments. Owner: ASJ (Code writes). Window: Thu Oct 8.

- 19. $12 bundle on Payhip. Owner: ASJ. Window: Fri Oct 9.

- 20. Count it: revenue minus costs. ≥ $100 → small ad test. < $100 → repeat 7 days, no new spend. Owner: ASJ + Code. Window: Sat Oct 10.

- 21. Set the approval rule for what Code may send, publish or buy. Owner: ASJ. Window: after testing (ASJ's timing).

- On hold: TikTok for Pearl and Eli. Needs a second phone number, which ASJ doesn't have. Owner: ASJ.

- On hold: Jade TikTok Business account. Needs business verification (LLC/EIN). Owner: ASJ.

- Later: ironic $14 Miss Pearl candle. Owner: ASJ. After income exists.

### 4. Learned skills and workflows (new this session)

#### 4.11 Skill: append-handoff-update

- Description: Add a dated session update to an existing HANDOFF.md without overwriting it, with a backup and verification.

- When: any time a handoff file already exists and needs a new session's information.

- Instructions:

  - Find HANDOFF.md and read the whole file. If it doesn't exist, create it and say so.

  - Check every copy (working folder, outputs, project doc) and the live plan doc for changes by anyone else. Compare checksums and the doc revision. Don't assume what's in a changed file until it's been read.

  - Back it up next to the original: HANDOFF_BACKUP_<YYYY-MM-DD_HHMM>.md.

  - Write the new section to a scratch file, then append it with cat >>. Never use a whole-file Write.

  - The new section starts with --- and ## Session update - <date time>. List outdated older content under "Changes since the previous handoff," one line each, and never edit the old text.

  - Verify: the first N bytes still match the backup (cmp -n), the new heading is the last section, and the size grew. Report the sizes before and after.

  - Sync copies (project doc) with the full appended file.

#### 4.12 Skill: tiktok-personal-account-sales-path

- Description: Sell from a TikTok personal account with under 1,000 followers (no bio link, no Business account).

- When: the creator has no LLC/EIN for TikTok business verification, or no second phone number.

- Instructions:

  - Caption CTA: "comment [KEYWORD] and I'll send it" or "link's in my IG bio @[handle]."

  - Pin a comment with the full product URL on every video.

  - DM the link to everyone who comments the keyword (by hand unless an AutoDM tool is approved).

  - Push followers to Instagram, where the bio link works at any follower count.

  - Re-check once the account hits 1,000 followers. A personal account gets the bio link field at that point.

### 5. Code and configuration (written this session)

All of these ran in Claude's cloud workspace. None touch ASJ's computer or any external service.

Check the time, list the folders, and compare the handoff copies (confirms nothing was changed by anyone else):

TZ=America/Los_Angeles date '+%Y-%m-%d_%H%M %Z'

ls -la /mnt/user-data/outputs/ /home/claude/

wc -c /mnt/user-data/outputs/HANDOFF.md /home/claude/HANDOFF.md

md5sum /mnt/user-data/outputs/HANDOFF.md /home/claude/HANDOFF.md

Back up before appending (in /mnt/user-data/outputs/):

cd /mnt/user-data/outputs && cp -p HANDOFF.md HANDOFF_BACKUP_2026-10-04_0843.md \

&& wc -c HANDOFF.md HANDOFF_BACKUP_2026-10-04_0843.md \

&& md5sum HANDOFF.md HANDOFF_BACKUP_2026-10-04_0843.md

Append, then verify the original bytes are untouched and the new heading is last:

cd /mnt/user-data/outputs

cat "$SCRATCH/update_2026-10-04.md" >> HANDOFF.md

cmp -n "$(wc -c < HANDOFF_BACKUP_2026-10-04_0843.md)" HANDOFF.md HANDOFF_BACKUP_2026-10-04_0843.md && echo "original intact"

grep -n '^## Session update' HANDOFF.md

wc -c HANDOFF_BACKUP_2026-10-04_0843.md HANDOFF.md

cp HANDOFF.md /home/claude/HANDOFF.md   # keep the working-folder copy identical

Plan-doc change check (Claude Docs read, view since revision 25). It returned no changed blocks:

{"ref":{"object":"node","id":"a1d6c8bb-6c0d"},"engine":"prose",

"container":{"kind":"project","id":"2013090d-e0b6-4539-b803-7890fb40510f"},

"payload":{"kind":"view","sinceRev":25}}

The Postiz configuration is unchanged from the original §5 (not re-queried this session).

### 6. Architecture and plans (current)

Claude/Code: product PDFs, Payhip copy, scripts, analysis  (no sending, publishing or buying)

│

├─► Gemini (free): character sheets → scene images            [ASJ]

├─► CapCut (free): 9:16 videos, AI label                       [ASJ]

│   Higgsfield Starter (~$15, optional, after Mon payout)      [ASJ decides]

├─► Scheduling: Postiz (trial ending ~Mon Oct 5) or native schedulers  [ASJ]

│

├─► Instagram ×3 (bio link → Payhip)   @misspearlmoney · @grandpaeliliveswell · @jadegxlden

└─► TikTok: Jade only, PERSONAL account → pinned-comment link / "link in IG bio" / keyword DM

│

▼

Payhip free (3 products + $12 bundle) → nightly tracker → Wed leader (IG numbers) → Sat count

File locations:

| File | Location |
| --- | --- |
| HANDOFF.md (updated, delivered) | /mnt/user-data/outputs/ |
| HANDOFF_BACKUP_2026-10-04_0843.md | /mnt/user-data/outputs/ |
| Working copy of HANDOFF.md | /home/claude/ |
| Project doc claude/HANDOFF.md | "Ai creators" Project |
| Plan doc "AI Influencer 7-Day Sprint" | Claude Docs artifact |

### 7. Accounts, tools and handles (names only)

- Instagram: @misspearlmoney · @grandpaeliliveswell · @jadegxlden

- TikTok: Jade (personal account; handle still not given)

- Tools: unchanged from original §7. TikTok Business account is ruled out for now.

- Project: "Ai creators" (claude.ai)

### 8. Open questions and blockers

- Jade's TikTok handle: not given.

- Instagram setup: still unconfirmed whether bios are pasted, profile pics are set, and the Creator switch is done.

- Character sheets and scene images: done? No files shared with Claude yet, so the products can't use the real character images until ASJ shares them. Code will build without photos or with placeholders unless ASJ sends them.

- Bank transfer ($40): arrival date not given.

- Approval rule: ASJ will define it after testing. Until then: no sending, publishing or purchasing.

- Postiz: trial ends ~Mon Oct 5. Can it take 4 more channels, and will ASJ pay after? Unknown.

- Payhip store structure (one store vs. per character): undecided.

- TikTok for Pearl and Eli: blocked indefinitely (no second phone number).

- Jade TikTok link: blocked until 1,000 followers or business verification.

- StarNest: not discussed. Nothing to hand off.

- Higgsfield Starter price: ~$15 per third-party sources. Confirm at checkout (ASJ only).

### 9. First 3 things for Code to do

- Build the 3 printable PDF products tonight (Petty Budget $5, 30-Day Old Ways Reset $7, Situationship Detox $6). Ask ASJ for the character sheet images first if they're ready. Otherwise build text-and-design versions with a cover-image slot. Deliver the files to ASJ only. No uploads.

- Draft the Payhip listing copy for all 3 products and the $12 bundle as text for ASJ to paste. Don't create the store.

- Write the first 15 scripts (5 per character). Jade's TikTok versions use the personal-account CTA (keyword comment / "link in my IG bio").

### Folder check at this update

- /mnt/user-data/outputs/: before this update it held only HANDOFF.md (28,009 bytes, written by Claude Oct 4 08:09 UTC-7). Added now: HANDOFF_BACKUP_2026-10-04_0843.md (by Claude).

- /home/claude/: HANDOFF.md, Claude's own copy (same checksum as the outputs copy before the update). The rest are hidden system/config folders that existed before this project.

- Project "Ai creators": claude/HANDOFF.md matches the original handoff text exactly.

- Plan doc: no changes since Claude's last edit (revision 25).

- No files were added or changed by anyone other than Claude since the last handoff.