# HANDOFF.md

Prepared Sunday, October 4, 2026 (founder timezone: America/Los_Angeles). Scope: only what happened in this conversation. Anything not established here is listed under "Open questions". "Me" in this file means the founder (ASJ / Jonelle). "Code" means Claude Code.

## 1. Project overview

### 1A. StarNest (17-part venture portfolio) - the active focus

What it is. StarNest is a portfolio of 17 AI-assisted venture tracks plus a shared research and distribution function, per STAR NEST MASTER CONTEXT.md (snapshot date Oct 4, 2026, 2,919 lines). The governing rule: do not automate an unproven business; automate a proven process (Discover, Validate, Test, Sell, Measure, Automate, Scale or kill). It is not 17 revenue-producing businesses.

Why. First measurable AI-assisted revenue plus reusable SOPs that can later become StarNet OS agent workflows. Recorded targets (plans, not results): $0 starting cash, $100 to $200 tool fund by Day 14, at least $1,000 collected by Day 30. Weekly outreach target 100 touches; 50 touches is the minimum checkpoint before changing the offer, message or audience.

Master context findings that matter.

- 28 working Markdown files in the local venture folders are empty. Detailed playbooks live in Notion (parent page "StarNest AI Income Playbook", 17 child pages).

- The shared API layer (three guides under SHARED/) is written locally; no provider has been selected, installed or tested.

- Recommended money plan: one primary cash offer plus one background asset. AI Training and Consulting is rank 1 (score 99); Google Business Profile Optimization is the secondary candidate (score 95).

What I read of the master context. Lines 1 to 775 (sections 1 to 10 plus the start of section 11, including the AI Books playbook) and lines 2440 to 2509 (venture 17, AI Training and Consulting). I did NOT read the other 16 venture playbooks, section 12 (Google Sheet values), section 13 (local file tree) or section 14.

Current status (venture 17, AI Training).

- Primary offer chosen by me: AI Training (see section 2).

- OFFER.md, WORKSHOP.md, AUDIT.md were empty and are now populated as drafts (prices are unapproved proposals).

- 20 prospects researched from the businesses' own public websites: 15 with a public email, 5 reachable only by phone or contact form.

- Tailored outreach email drafts written for the 15 emailable prospects. None sent.

- Sales log CSVs created with prospects pre-loaded. No outreach, replies, calls or cash have been recorded.

- Nothing has been sent, no payment path exists, no sample/proof artifact exists yet.

### 1B. AI influencer project - came up early, then redirected

Source and caveat. This came from a saved memory note I read (/areas/ai-influencers.md), not from anything I was told in this conversation. I used it to write a 48-hour plan; you then pointed out the project I should have been working from was StarNest (the file you meant is STAR NEST MASTER CONTEXT.md). The influencer plan was never confirmed or revisited.

What the note says.

- Plan to recreate the full AI-influencer creation flow from a YouTube "7-day AI influencer challenge" (spy on competition, character ideas, photos, scripts, voice, video, launch, monetize), changing the content created.

- AI is disclosed openly on all accounts.

- Three characters, all Black with a range of skin tones, aimed at Black audiences: Miss Pearl (older woman, comedy, fair-skinned), Grandpa Eli (older man, health and wellness, dark-skinned, rural Georgia), Jade (young woman, lifestyle and relationships, brown-skinned, Oakland).

- Instagram handles created: @misspearlmoney, @grandpaeliliveswell, @jadegxlden.

- Platforms: Instagram and TikTok, posting via Postiz. Goal: about $100 in sales in the first week (started Oct 3, 2026) with no ad spend, then reinvest into ads.

- DJ J Carbon TikTok is not banned but gets very low views; you suspect your IP is flagged as a bot and want the new accounts unaffected.

Status. Only the draft 48-hour plan exists (below, section 3 "Parked"). Nothing was executed. The StarNest master context separately lists local reference images for Grandpa Eli, Jade (V1, V2) and Miss Pearl under 02-ai-creators/, and says Jade is the only persona tied to a live-page strategy. Whether these are the same characters as the influencer project is not confirmed.

## 2. Decisions made

| Decision | Reason |
| --- | --- |
| Primary offer = AI Training (AI Training and Consulting, venture 17) | It is the master context's default and top-ranked cash lane; you confirmed "yes, we can do AI training" once I explained "primary offer" means the first service we try to sell |
| Target buyer (starting hypothesis) = small office-based businesses of about 3 to 25 people with lots of routine writing: property managers, small accounting/tax firms, small real estate offices and small insurance agencies, in Oakland/East Bay and Mariposa/Yosemite area | You did not know whom to pick and asked for a recommendation; I proposed this. You then asked for more prospects in the same mold, which I read as acceptance. It is untested, not validated demand |
| Outreach channel = email | Your stated choice |
| Prospect collection = manual reading of each business's own public website, small batches, no bulk scraping | You asked about scraping; the shared AGENTS.md rules say to prefer official APIs, avoid collecting structured data at scale manually, and check the SHARED catalog first. Sites that block automated reading (robots.txt, 403) were skipped, not worked around |
| Emails are tailored per business (each uses a detail from that business's own site) | Your explicit request |
| Nothing is sent without your approval; I draft, you review and send | Your explicit instruction. Also matches the master context guardrail (no inferred permission to contact prospects) |
| Working hours: your own work 12 to 4 p.m. and 8 p.m. to midnight; buyer-facing work 9 to 5 | Your stated availability for the next week |
| Prices in OFFER.md are proposals only | Master context says record unapproved prices as proposals; no price was approved |
| Offer shape: 90-minute workshop ("AI Workday Tune-Up"), optional workflow audit, ladder workshop -> audit -> roadmap -> implementation | Matches the venture 17 service ladder in the Notion snapshot |
| Cash first: one primary offer plus at most one background content lane (Jade or travel TikTok) | Master context money plan; do not launch all 17 ventures at once |
| Spend $0 unless essential and approved; tool spend capped at 50% of cash collected | Master context constraint |
| Keep existing folder names and media; do not restructure the Sheet silently | Master context guardrail |
| Influencer project: AI disclosed openly, platforms Instagram + TikTok, posting through Postiz | Recorded in the saved memory note (not re-confirmed in this conversation) |
| Saved all files locally in the connected 17-ai-training folder | Your request ("save the files local please") |
| New files: separate batch-2 sales log instead of editing the batch-1 CSV | Avoid overwriting anything you may have edited |

## 3. Actionable items (priority order)

Dates: today = Sunday Oct 4, 2026. Windows below follow the 48-hour plan: Today (Sun Oct 4), Monday Oct 5, Tuesday Oct 6 morning. Buyer-facing sending only 9 to 5 on business days (Monday, Tuesday). Tuesday to Thursday mornings were suggested as the best send times, so some sends may roll past Tuesday.

### Gating decisions and edits (must come first)

- 1. Approve or edit the offer and set real prices. Owner: me. Next step: read OFFER.md, pick exact prices (proposed: pilot $150 to $300, standard team workshop $400 to $600, audit add-on $250 to $500). Dependencies: none. Window: before Day 4 paid ask; ideally tonight so drafts can go out Monday.

- 2. Choose a payment path. Owner: me. Next step: pick a provider and set up a way to collect payment (the source files do not name one). Dependencies: item 1. Window: before Day 4 (Wed Oct 7 under the Day 1 = Sun plan).

- 3. Fill in [BUSINESS NAME] and [ADDRESS] in every email draft. Owner: me. Next step: choose the business name and a real mailing address (needed for commercial email, plus the opt-out line already included). Dependencies: none. Window: before the first send.

- 4. Verify the Community Realty email. Owner: me (Code can help). Next step: confirm info@mycommunityrealty.com against their site; the site I read was crpmrealty.com and the email domain differs. Window: before sending draft 4.

- 5. Re-check every email address on each business's own site before sending. Owner: me. Next step: open each site, confirm the address. Window: before each send.

### Day 1 (Sunday Oct 4 per the plan; roll forward if not done)

- 6. Identify 5 warm leads from your own network. Owner: me. Next step: list five people or businesses you know who might want AI training; Code can draft tailored messages once named. Dependencies: none. Window: Today. (No warm leads have been named in this conversation.)

- 7. Review and send Batch 1 emails. Owner: me. Next step: review OUTREACH_DRAFTS_BATCH1.md, edit, send drafts 1 to 5 yourself during business hours. Dependencies: items 3, 4, 5. Window: Mon Oct 5, 9 to 5.

- 8. Contact the two Batch 1 prospects with no public email. Owner: me. Next step: HCCPA Inc, (510) 251-6228 or its contact form; the Oakland accounting firm at 4225 Telegraph Ave, 510-652-6213. Window: business hours.

- 9. Build one small proof sample. Owner: Code drafts, me approves. Next step: create a before/after example (e.g. rough owner-update note into a clear email, or a long email thread summary) using only invented sample text, saved beside WORKSHOP.md. Dependencies: none. Window: Today or Monday.

- 10. Start using the sales log. Owner: me (Code can maintain). Next step: record first contact dates and replies in SALES_LOG.csv and SALES_LOG_BATCH2.csv. Window: from the first send.

### Day 2 (Monday Oct 5)

- 11. Send Batch 2 emails (drafts 6 to 16). Owner: me. Next step: review OUTREACH_DRAFTS_BATCH2.md, send during business hours. Dependencies: items 3 and 5. Window: Mon Oct 5 and Tue Oct 6, 9 to 5.

- 12. Make the phone/form contacts from Batch 2. Owner: me. Next step: Better Books Bookkeeping (209.966.2800), Catheys Valley Real Estate (209.777.3100), Real Property Management Pacific (contact form), Jeffrey Shaw at Farmers (209-742-6660 or form). Scripts are in the batch-2 file. Window: business hours; the last two are lower fit and go last.

- 13. Follow up on Day 1 touches and add 10 new prospects (about 20 touches total). Owner: me sends; Code finds new prospects. Next step: ask Code for another batch of prospects when Batch 1 and 2 are used up. Window: Monday.

- 14. Produce two tailored samples or mini workflow audits for the best-fit prospects. Owner: Code drafts, me approves. Next step: pick two high-fit prospects (e.g. Selborne Properties, Openworld, SLPM, Marquardt, Asnani CPA, Summit Tax, Busy Bee Accounting, Yosemite Realty were rated High), draft a short mini-audit from their public site only. Dependencies: item 9. Window: Monday.

- 15. Record every reply and objection in the sales log. Owner: me. Window: Monday onward.

- 16. Optional background content lane: one Jade or travel TikTok post. Owner: me. Next step: pick one; record account, date, post ID, hook, retention. Master context says keep this to a manageable cadence and do not combine metrics across accounts. Window: Monday, only after revenue work is moving.

### Day 3 (Tuesday Oct 6, morning)

- 17. Day 3 touches: 10 new prospects and 10 follow-ups. Owner: me sends; Code supports. Dependencies: items 7, 11, 13. Window: Tue Oct 6.

- 18. Tighten the offer using objections logged so far. Owner: Code and me. Next step: update OFFER.md from the log. Target by end of Day 3: two positive replies or one call.

- 19. Prepare the Day 4 paid-next-step ask and a delivery checklist. Owner: Code drafts, me approves. Next step: finalise the checklist in WORKSHOP.md and a proposal/payment ask template. Dependencies: items 1, 2.

- 20. Send follow-ups 3 to 4 business days after first contact. Owner: me. Next step: use the follow-up template at the bottom of OUTREACH_DRAFTS_BATCH1.md. Window: after the first sends.

### Housekeeping and dependencies

- 21. Review the weekly checkpoint. Owner: me and Code. Next step: after 50 qualified touches (minimum) and toward the 100-touch weekly target, diagnose targeting/message if no replies; offer, trust or price if interest does not convert; package scope if delivery is slow. Window: Day 7 (about Sat Oct 10).

- 22. Read the SHARED API files before any scraper, data tool purchase or integration. Owner: Code. Next step: read SHARED/API_CATALOG.md, SHARED/API_SELECTION_RULES.md, SHARED/INTEGRATION_IDEAS.md (not yet read; I could not open them). Dependency: folder access. Window: before building anything beyond manual research.

- 23. Update the durable master context. Owner: Code. Next step: record what changed, why, evidence, owner, next action, date, keeping completed work separate from proposed work (master context section 14 and section 9, step 10). Window: after the first sends.

- 24. Save durable project docs to the claude.ai Project "AI Business Directives". Owner: Code. Next step: write the offer and handoff docs with project_write (the project had 0 docs). Optional.

- 25. Reconnect or repair the Documents/AI Business Derivatives  folder link. Owner: me. Next step: the original connected path (note trailing space) failed with "no longer accessible"; the new Downloads/.../17-ai-training connection works. Only needed if you want files in the Documents location too.

- 26. Optional: ask Code for Batch 3 prospects. Owner: me asks, Code does. Next step: 10 to 15 more from public websites, same method. Window: when Batch 1 and 2 are sent.

### Parked: AI influencer plan (drafted, never confirmed)

Do not start these unless you say the influencer project is also in scope this week. The draft plan was:

- Today: switch the three Instagram accounts to Professional, add an "AI-generated character" disclosure to each bio, add photo/name/link (owner: me).

- Today: create matching TikTok accounts using a clean device or network, separate from DJ J Carbon (owner: me).

- Today: one-page character sheet per character (look, age, backstory, voice, catchphrases) and a reference photo set of about 8 to 10 images per character (owner: me, Code assists).

- Today: competitor scan of 5 top accounts per niche (owner: Code).

- Today: connect Postiz to the Instagram and TikTok accounts and test post (owner: me; the Postiz tools were disconnected at the end of this session).

- Today: choose one low-cost offer per character (affiliate, digital guide or template) and check its terms (owner: me).

- Monday: 7 scripts per character (21 total), voice choice, first 3 videos per character (9), captions with AI disclosure, schedule in Postiz, comment-reply plan (owner: me, Code drafts).

- Tuesday morning: confirm posts live, start a tracking sheet, review the first 24 hours, plan next batch (owner: me).

## 4. Learned skills and workflows

Each entry can be saved as a skill.

### Skill: starnest-context-navigator

Description: Navigate a very large handoff or master-context file without reading all of it. Use when a project file is thousands of lines long and you only need one section. Instructions:

- Read the first ~775 lines (overview, priorities, plan, guardrails, open questions).

- Grep for headings (^### 1[1-4]\.|^## 1[2-4]\.) to get line numbers for each section.

- Read only the section you need with offset/limit (e.g. venture 17 was lines 2440 to 2509).

- Tell the user which parts you did not read.

### Skill: small-batch-prospect-research

Description: Build a prospect list from public websites without bulk scraping, respecting the shared API rules. Use before any outreach list is created. Instructions:

- Confirm the buyer niche and geography.

- Run a web search per niche (e.g. "small CPA bookkeeping firm Oakland California team contact", "independent insurance agency Mariposa California contact email").

- Fetch each business's own website with a prompt asking for: firm name, city, services, size, public email, phone, address, and one personalizing detail.

- If a site returns ROBOTS_DISALLOWED or a 403, skip it. Do not work around it with curl, Python or archives.

- Record only what the page says; mark unknown fields as "none public". Do not guess emails.

- Prefer businesses with a public email; list phone/form-only businesses separately with a call script.

- Flag lower-fit prospects (franchises, national-insurer agents, large firms).

- Record the source and date (Oct 4, 2026) in the sales log.

### Skill: tailored-cold-email-draft

Description: Write one short personalized outreach email per business from facts on their own website. Use for AI training outreach (or any service outreach) that the founder will send personally. Instructions:

- Subject: plain and specific to the business type (e.g. "Saving time on owner and tenant communication").

- Opening line: one verifiable detail from their site (e.g. "more than 850 rentals", "serving the Bay Area since 1911", "four CPAs"). Do not invent flattering claims.

- Middle: what the workshop does (90 minutes, their own sample tasks, reusable templates, rules for confidential data, human review before sending).

- Close: one low-pressure ask (15-minute call or a one-page outline).

- Signature: sender name, [BUSINESS NAME] | [ADDRESS].

- Opt-out line: Reply "no thanks" and I won't contact you again.

- Tone adjustments: law firms get a safe-use emphasis and an acknowledgement of firm policy; franchise/national-insurer agents get a note that corporate rules may apply.

- Verify every claim against the fetched page before delivering. Never send; the founder reviews and sends.

### Skill: outreach-sales-log

Description: Track a seven-day outreach sprint. Use when the master context calls for a dated sales record. Instructions: Create a CSV with the columns in section 5, one row per prospect, source and date filled in, other columns blank until an event happens. Log new prospects and follow-ups separately, and count both. Review at 50 touches (minimum) and 100 touches (weekly target).

### Skill: ai-training-workshop-delivery

Description: Deliver the 90-minute "AI Workday Tune-Up" workshop. Use once a client says yes. Instructions:

- Pre-call (15 min): ask the three tasks that take the most time, tools in use, anyone already using AI; collect 2 to 3 non-confidential sample tasks 48 hours ahead.

- Agenda: 0:00 to 0:10 what AI is good and bad at; 0:10 to 0:25 the 4-part prompt (role, task, context, format); 0:25 to 0:55 hands-on with their tasks; 0:55 to 1:10 safe-use rules; 1:10 to 1:20 build 3 to 5 reusable templates; 1:20 to 1:30 Q&A and audit offer.

- Deliver within 24 hours: one-page "how we use AI here" guide, 3 to 5 prompt templates, 7-day follow-up email.

- Log delivery hours and cash collected. Ask (do not assume) for a testimonial or referral.

### Skill: ai-workflow-audit

Description: Follow-on audit after a workshop shows a clear need. Instructions: Interview (typical week, repeated tasks, stalled handoffs, longest writing/research tasks, recurring mistakes, confidential data). Deliver one table: current state, pain point, possible AI use case, estimated impact (labeled as an estimate), complexity, priority. No guaranteed savings. Recommend implementation only for validated, low-risk cases.

### Skill: seven-day-ai-training-sprint

Description: Run the recorded seven-day lock-in plan for the cash offer. Instructions: Day 1: five warm leads plus ten qualified prospects (15 touches), one-page offer, payment path. Day 2: ten new prospects plus Day-1 follow-ups, two tailored samples or mini-audits (about 20 touches). Day 3: ten new prospects and ten follow-ups, tighten offer from objections, aim for two positive replies or one call. Day 4: ask directly for a paid next step, delivery checklist. Day 5: continue ten new prospects, deliver first sale, seek testimonial/referral. Day 6: follow up warm leads, build a reusable delivery SOP, optionally batch three posts. Day 7: follow-ups, ten new prospects, review at least 50 qualified touches, decide continue or revise.

### Skill: local-folder-delivery-via-device-bridge

Description: Save finished files to the user's connected folder. Use when the user wants files saved locally. Instructions:

- List the destination with device_list_dir first; note sizes and mtimeMs of existing files.

- Write finished files under /mnt/user-data/outputs/.

- Commit with device_commit_files using stagedPath and devicePath. For files that already exist (here, empty placeholders), pass expectedMtimeMs from the listing so a newer user edit is never overwritten. New files need no guard.

- Report folder and file names in plain language. If a commit is rejected, say which file stayed in the conversation and why.

- Gotcha: the original folder name ends with a trailing space ("AI Business Derivatives "); lookups with or without it failed until the user connected the 17-ai-training folder.

### Skill: evidence-first-handoff-reporting

Description: Report status without inflating it. Use when summarizing StarNest progress. Instructions: Separate source claims, observed evidence, assumptions and estimates. Targets and scorecards are not results. A folder, instruction file or planning row is not a finished business system. Say plainly what was not read or not verified.

### Lessons from mistakes this session

- I answered the first "give me a to-do list" request using the influencer memory note instead of what the attached file said. Before building a plan, confirm which project is meant, and base it on the file the user attached.

- The first attached file (AGENTS.md) was short shared rules; the real project brief was a different file. Ask for the right file rather than inferring.

## 5. Code and configuration

No scripts, applications or API integrations were written. Everything delivered is Markdown or CSV. Full text lives in the files themselves (not duplicated here); the pieces below are the reusable structures.

### 5.1 Sales log schema (CSV header)

Used in both SALES_LOG.csv and SALES_LOG_BATCH2.csv. Fields come from the master context (section 9, step 5).

prospect_business,source,fit,channel,first_contact,follow_up,reply,positive_signal,sample,call,proposal,amount,cash_collected,delivery_hours,next_action

Row example (as written):

Selborne Properties,Own website (Oct 4 2026),High,Email info@selborneproperties.com,,,,,,,,,,,Review and send draft 2

### 5.2 Email template skeleton (from the drafts)

Subject: <specific subject>

Hello <name or team>,

<one verified detail from their own website>. <why that implies routine writing/admin work>.

I teach small teams to use AI tools (Claude, ChatGPT) to draft and tidy routine messages and summarize long threads, with a person reviewing everything before it goes out. The session is 90 minutes, uses your own non-confidential sample tasks, and ends with reusable templates and simple rules for what never goes into an AI tool.

Would a 15-minute call or a one-page outline be useful?

Thank you,

Jonelle Alleyne

[BUSINESS NAME] | [ADDRESS]

Reply "no thanks" and I won't contact you again.

### 5.3 Follow-up template

Subject: Re: [original subject]

Hello, just following up in case my note got buried. I'm offering a short, practical AI session for small teams and would be glad to send a one-page outline. No pressure either way.

Jonelle Alleyne | [BUSINESS NAME] | [ADDRESS]

Reply "no thanks" and I won't contact you again.

### 5.4 Device-bridge commit call (how files were saved locally)

{

"files": [

{

"devicePath": "/Users/djjcarbon/Downloads/AI Business Derivatives /AI Workforce Assets/StarNest_Projects/17-ai-training/OFFER.md",

"stagedPath": "/mnt/user-data/outputs/AI-Training/OFFER.md",

"expectedMtimeMs": 1791094419503

}

]

}

Same pattern for WORKSHOP.md and AUDIT.md (both had expectedMtimeMs 1791094419503 and size 0). The other four files were new and had no expectedMtimeMs.

### 5.5 Grep used to index the master context

pattern: ^### 1[1-4]\.|^## 1[2-4]\.

Result: section line numbers (e.g. 11.17 AI Training at line 2440, section 12 at 2510, section 13 at 2709, section 14 at 2910).

### 5.6 File inventory (what each file does and where it lives)

Local folder (on the founder's computer): /Users/djjcarbon/Downloads/AI Business Derivatives /AI Workforce Assets/StarNest_Projects/17-ai-training/

| File | Purpose |
| --- | --- |
| OFFER.md | Offer, buyer hypothesis, deliverables, exclusions, proposed pricing, approvals needed |
| WORKSHOP.md | 90-minute agenda, pre-call, deliverables, delivery checklist, proof-sample idea |
| AUDIT.md | Workflow audit template and checklist |
| OUTREACH_DRAFTS_BATCH1.md | Prospects 1 to 7, email drafts 1 to 5, follow-up template, send checklist |
| OUTREACH_DRAFTS_BATCH2.md | Prospects 6 to 20, email drafts 6 to 16, phone/form scripts 17 to 20 |
| SALES_LOG.csv | Batch 1 prospects, 7 rows |
| SALES_LOG_BATCH2.csv | Batch 2 prospects, 15 rows |
| CLAUDE.md (existing, not edited) | Shared API rules, 876 bytes when listed |

Copies also exist in the cloud session under /mnt/user-data/outputs/AI-Training/ and this file at /mnt/user-data/outputs/HANDOFF.md.

Note the numbering overlap: Batch 1 prospects are numbered 1 to 7; Batch 2 starts again at 6 in its table. Treat them as separate lists (Batch 2 rows are drafts 6 to 16 and scripts 17 to 20).

### 5.7 Prospect register (public contact details as read on Oct 4, 2026)

Batch 1:

| Business | City | Contact | Notes |
| --- | --- | --- | --- |
| Prestige Accounting and Tax Advisors | Oakland / Concord | info@kennyahncpa.com | clients in real estate, healthcare, law, media |
| Selborne Properties | Oakland | info@selborneproperties.com | 850+ rentals, 13+ years |
| Prime Property Management Corporate | Oakland | Hello@PrimePropertyPM.com | IREM-accredited, HOA and commercial |
| Community Realty Property Management | Oakland | info@mycommunityrealty.com (verify) | serving the Bay Area since 1998 |
| Yosemite Realty | Mariposa / Oakhurst | YosemiteRealtyGroup@gmail.com | relocation and fire-loss clients |
| HCCPA Inc (Vivian Chen, CPA) | Oakland / Burlingame | phone (510) 251-6228, no public email |  |
| Accounting firm at 4225 Telegraph Ave | Oakland | phone 510-652-6213, no public email | page did not state the firm name; the site fetched was ogbodocpa.com (so likely Christopher Chime Ogbodo & Associates, inference) |

Batch 2:

| Business | City | Contact | Notes |
| --- | --- | --- | --- |
| Openworld Properties | Oakland | info@openworldproperties.com | tech-forward |
| SLPM Property Management | San Leandro | info@slpm.com | since 1978 |
| The Lapham Company | Oakland | info@laphamcompany.com | established 1911 |
| Marquardt Property Management | Oakland | info@mpmoakland.com | family-owned since 1960 |
| Asnani CPA | Hayward | sasnani@asnanicpa.com | outsourced accounting |
| Hwang, Choi, Kim & Jeon CPAs | Oakland | info@hwangchoicpas.com | four CPAs |
| Summit Tax & Financial Services | Mariposa / Fremont | info@summit-tax.com | has a Mariposa office |
| Harp Insurance Services | Mariposa | lharp649@earthlink.net | 25+ years |
| Macaulay Insurance Agency | Oakhurst | susan@macaulayins.com | commercial and vacation-rental lines |
| Busy Bee Accounting Services | Oakhurst | info@busybeeaccounting.com | four-person team |
| Berliner Cohen LLP (Mariposa) | Mariposa | kimberly.flores@berliner.com | larger law firm, lower odds |
| Better Books Bookkeeping | Mariposa | phone 209.966.2800 | no public email |
| Catheys Valley Real Estate | Catheys Valley | phone/text 209.777.3100 | no public email |
| Real Property Management Pacific | Oakland | contact form | franchise, lower fit |
| Jeffrey Shaw, Farmers Insurance | Mariposa | (209) 742-6660 or agent form | national insurer, lower fit |

Skipped or unreadable during research: etchiecpa.com and taxandbusinessservice.com (blocked automated reading), dimovtax.com (page returned 404), graystoneriskman.com (403), millerwhitecpa.com (could not be read), oaklandpropertymanagement.co first appeared in results and was readable (Marquardt), State Farm agent Roger Brunelle (found but not used; no public email, and not added).

## 6. Architecture and plans

Layers (from the master context).

- Founder: decision owner and the only sender of outreach.

- Claude and Codex: Claude is researcher, analyst, strategist, editorial partner, SOP author; Codex handles local file implementation, code, apps, integrations and verification. Neither should claim to have edited a file, sent anything or connected an account without readback evidence.

- Notion: strategy and 17 venture playbooks ("StarNest AI Income Playbook").

- Google Sheet: "StarNest 30-Day Money Plan" (six tabs; I did not read them).

- Local project root: StarNest_Projects/ with numbered venture folders such as 17-ai-training/ and 02-ai-creators/. Every folder's CLAUDE.md points at ../SHARED/ API guides.

- StarNet OS: future orchestration; not verified as configured.

Data flow for this week's sprint. public business websites -> prospect register (Claude, read-only research) -> tailored drafts (Claude) -> founder review and send (email, 9 to 5) -> replies and events logged in the sales CSVs -> objections feed back into OFFER.md -> proposal and payment ask (Day 4) -> workshop delivery (WORKSHOP.md checklist) -> cash collected and hours logged -> master context updated.

Where files live. Working copies in the cloud session (/mnt/user-data/outputs/); durable copies in the local 17-ai-training folder; strategy in Notion; planning numbers in the Google Sheet; saved notes about you in the memory store (including a StarNest note under the AI Business Directives Project).

Influencer posting flow (from the memory note). Characters -> Instagram and TikTok accounts -> Postiz auto-uploader. Postiz tooling was connected earlier in the session and was reported disconnected later. Nothing was posted.

Weekly rhythm. Your own deep work: 12 to 4 p.m. and 8 p.m. to midnight. Buyer-facing sending and calls: 9 to 5. Suggested: review drafts at night, send in the morning.

## 7. Accounts, tools and handles (names only)

- Founder identity: goes by ASJ; middle name Jonelle; email account asjalleyneholdings@gmail.com; DJ name DJ J Carbon. Businesses: ASJ (parent) and Alphia's Movers LLC.

- Instagram (influencer project): @misspearlmoney, @grandpaeliliveswell, @jadegxlden.

- TikTok accounts named in the master context: DJ J Carbon main account, DJ J Carbon BTS/backup page, Travel TikTok, Jade AI Creator TikTok, Carbon Garden.

- Posting: Postiz.

- Strategy and planning stores: Notion ("StarNest AI Income Playbook", 17 child pages), Google Sheet ("StarNest 30-Day Money Plan"), claude.ai Project "AI Business Directives".

- AI tools reported by you: ChatGPT Plus and (reported, not verified) Claude Pro; Claude and Codex as working agents; StarNet OS as a future layer.

- Gmail: an account is connected to this session; no mail was read or sent.

- Local: MacBook "djs-macbook-pro-local"; connected folder 17-ai-training (Downloads path in section 5.6).

- Mentioned as ideas only in the master context (not set up): transcript services (Arcmira, BulkTranscripts, TranscriptYT, TubeToTranscript, VidWords), public-apis directory.

- No credentials, tokens or API keys appear in this file.

## 8. Open questions and blockers

- Final prices and payment provider. Not decided. Blocks the Day 4 paid ask.

- Business name and mailing address for emails. Not given. Blocks sending.

- Warm leads. None named. Day 1 calls for five.

- Buyer niche. Chosen by recommendation and implicit acceptance; never explicitly confirmed. Confirm or change before Batch 3.

- Which email address for Community Realty is right. Domain mismatch.

- Who the 4225 Telegraph Ave accounting firm is. The page did not state it; my guess (ogbodocpa.com) is an inference.

- Which project(s) are in scope this week. StarNest AI Training is the active work. Is the AI influencer project in scope at the same time, and are its three characters the same as the Grandpa Eli, Miss Pearl and Jade reference sets in 02-ai-creators/?

- Influencer details never confirmed in this conversation. Accounts, character details, Postiz setup status and the $100 week-one goal came from the saved memory note.

- 17-ai-training/CLAUDE.md status. It was listed at 876 bytes earlier, but a later session notice said that instruction file was no longer present. Check whether it still exists and whether it still points to ../SHARED/.

- SHARED/ files. API_CATALOG.md, API_SELECTION_RULES.md, INTEGRATION_IDEAS.md have not been read (I could not open them). Needed before any scraper, data tool or integration.

- Folder access. The Documents/AI Business Derivatives  link was reported as no longer accessible. Only 17-ai-training is currently connected. If you want other venture folders updated, they must be connected.

- Unread master-context sections. The other 16 venture playbooks, the Sheet section 12 and the file tree section 13 were not read. Priorities elsewhere in the portfolio (Jade, travel TikTok, books, ghostwriting, GBP) are untouched.

- Hours available and laptop limits. You gave next-week hours but the master context's open question about laptop capacity (overheating reported) is unresolved.

- Outreach authorization scope. You said nothing is sent without your authorization. Unclear whether you will ever want Code to send emails after approval, or only draft.

- Lower-fit prospects. Whether to pursue the franchise and national-insurer agents (RPM Pacific, Farmers) at all.

- Postiz connection. Postiz tools were still connecting, then reported disconnected. Whether it is linked to any account is unknown.

- Sales and cash since Oct 4. None recorded. Do not report planning targets as results.

## 9. First 3 things for Code to do

- Reconcile state before touching anything. List 17-ai-training/ on the device, confirm the seven files from section 5.6 are present and that CLAUDE.md exists or not, read OFFER.md and OUTREACH_DRAFTS_BATCH1.md, and read the three ../SHARED/ files if they are reachable. Report anything missing.

- Build the proof sample and a Day-4 proposal/payment-ask template. Draft one before/after example (invented sample text only) and a one-page proposal template with placeholders for price and payment path, saved beside WORKSHOP.md. Do not send or publish anything.

- Prepare Batch 3 and day-by-day send sheet. Once the founder confirms the buyer niche, find 10 to 15 more prospects using the small-batch method in section 4 (public sites only, skip robots-blocked sites), append them to a new sales log CSV, and write tailored drafts. Also produce a one-page "send tonight, send tomorrow morning" schedule that fits the founder's 9 to 5 buyer window and 12 to 4 / 8 to midnight work blocks.

### Verification notes (self-check against the conversation)

- Every action item and every reusable process discussed in this conversation is included: the two 48-hour plans (influencer plan parked, StarNest plan active), prospect research, email drafting, the sales log, local saving, and the correction about which project was meant.

- Nothing in this file was sent, published or purchased. No outreach has happened.